TLS Cipher Hardening

OneNote-Compatible Internal Team Runbook

Mission: Remove weak Schannel cipher suites through OS-scoped Administrative Template GPOs while preserving tested application connectivity. Windows application servers are first; domain controllers are last.

| Field | Working value |
| --- | --- |
| Program owner | [Name / team] |
| Security lead | [Name / team] |
| Windows engineering lead | [Name / team] |
| Network / load balancer lead | [Name / team] |
| Change record | [CHG / project ID] |
| Target start | [Date] |
| Target completion | [Date] |
| Overall status | Not started / On track / At risk / Blocked / Complete |

# Operating assumptions

[ ] TLS 1.0 and TLS 1.1 are globally disabled.

[ ] TLS 1.2 is explicitly enabled.

[ ] TLS 1.3 remains enabled by the operating-system default on supported Server 2022/2025 systems.

[ ] Server scope is Windows Server 2019 through 2025.

[ ] Linux servers are not changed in the Microsoft phase, but Linux clients and applications must test connections to Windows endpoints.

# How to use this in OneNote

Insert the DOCX as a printout for a stable reference, or open it in Word and copy each numbered page into a separate OneNote page.

Keep the tables editable in OneNote and update owner, status, date, evidence link, and notes during each working session.

Use OneNote tags for To Do, Important, Question, and Contact, and link evidence instead of pasting sensitive logs.

Preserve the technical baseline page as read-only reference; track changes through decisions and action items.

Page 1 - Program Dashboard

Use as the landing page for weekly program review.

| Workstream | Owner | Status | Due | Latest update / next action |
| --- | --- | --- | --- | --- |
| GPO design and peer review | [Owner] | Not started | [Date] | [Update] |
| Security scan validation | [Owner] | Not started | [Date] | [Update] |
| Application inventory | [Owner] | Not started | [Date] | [Update] |
| Lab and pilots | [Owner] | Not started | [Date] | [Update] |
| Production Windows waves | [Owner] | Not started | [Date] | [Update] |
| Infrastructure services | [Owner] | Not started | [Date] | [Update] |
| Domain controllers | [Owner] | Not started | [Date] | [Update] |
| Exceptions and remediation | [Owner] | Not started | [Date] | [Update] |
| Closure evidence | [Owner] | Not started | [Date] | [Update] |

# This week's checkpoints

[ ] Application owners contacted and responses tracked.

[ ] Representative servers selected for every observed cipher pattern and OS version.

[ ] Test scripts, monitoring, and security rescans scheduled.

[ ] Rollback authority and reboot coordination confirmed.

[ ] Open decisions and exceptions have owners and due dates.

# Key metrics

| Metric | Target | Current | Evidence / notes |
| --- | --- | --- | --- |
| Servers inventoried | 100% | [ ] | [Link] |
| Applications with owner | 100% | [ ] | [Link] |
| Applications tested | 100% before production | [ ] | [Link] |
| Weak-cipher findings remediated | 100% or approved exception | [ ] | [Link] |
| Expired exceptions | 0 | [ ] | [Link] |

Page 2 - Technical Baseline

Approved cipher strings and the current-to-target change.

# Server 2019

GPO value: TLS_ECDHE_ECDSA_WITH_AES_256_GCM_SHA384,TLS_ECDHE_ECDSA_WITH_AES_128_GCM_SHA256,TLS_ECDHE_RSA_WITH_AES_256_GCM_SHA384,TLS_ECDHE_RSA_WITH_AES_128_GCM_SHA256

# Server 2022 and Server 2025

GPO value: TLS_AES_256_GCM_SHA384,TLS_AES_128_GCM_SHA256,TLS_ECDHE_ECDSA_WITH_AES_256_GCM_SHA384,TLS_ECDHE_ECDSA_WITH_AES_128_GCM_SHA256,TLS_ECDHE_RSA_WITH_AES_256_GCM_SHA384,TLS_ECDHE_RSA_WITH_AES_128_GCM_SHA256

| Current capability | Target state | Reason |
| --- | --- | --- |
| Modern suites already preferred | Only AES-GCM suites retained | Preserves modern negotiation |
| Static RSA present | Removed | Forward secrecy and scanner compliance |
| CBC / SHA-1 present | Removed | Avoid legacy construction findings |
| 3DES present on some endpoints | Removed | Obsolete 64-bit block cipher |
| PSK / NULL visible on three endpoints | Removed from policy | No normal dependency expected; confirm ownership |
| DHE present on some endpoints | Removed | ECDHE retained; aligns with newer Microsoft defaults |

# Baseline acceptance

[ ] Security approves the excluded-suite categories.

[ ] Windows engineering validates exact strings and GPO scope.

[ ] Network team confirms proxy/load-balancer overlap.

[ ] Change authority approves reboot and rollback requirements.

Page 3 - Application Inventory

One row per application or service dependency; link to detailed evidence if needed.

| Application / service | Business owner | Technical owner | Servers / OS | Inbound / outbound dependencies | Runtime / proxy | Risk | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| [App] | [Owner] | [Owner] | [Hosts / OS] | [Endpoints / ports] | [Java/.NET/OpenSSL/LB] | L/M/H | Not started |
| [App] | [Owner] | [Owner] | [Hosts / OS] | [Endpoints / ports] | [Java/.NET/OpenSSL/LB] | L/M/H | Not started |
| [App] | [Owner] | [Owner] | [Hosts / OS] | [Endpoints / ports] | [Java/.NET/OpenSSL/LB] | L/M/H | Not started |
| [App] | [Owner] | [Owner] | [Hosts / OS] | [Endpoints / ports] | [Java/.NET/OpenSSL/LB] | L/M/H | Not started |

# Owner readiness questions

[ ] What inbound TLS listeners and ports are used?

[ ] What outbound APIs, databases, LDAP, SMTP, webhooks, monitoring, backup, or vendor connections are used?

[ ] Are TLS versions or cipher suites hard-coded in the application, runtime, proxy, or appliance?

[ ] Does every hop support ECDHE with AES-GCM under TLS 1.2?

[ ] What certificate type is used: RSA or ECDSA?

[ ] Who will execute the complete functional test during the change window?

[ ] Is a low-frequency scheduled job part of the business workflow?

Special review: Confirm that no intentional PSK application dependency exists on the three endpoints whose export included PSK and NULL entries.

Page 4 - Test and Evidence Checklist

Use for each representative server and application before production promotion.

| Test item | Owner | Result | Timestamp | Evidence link / notes |
| --- | --- | --- | --- | --- |
| GPO applies to correct OS and OU | [Owner] | Pass / Fail | [Time] | [Link] |
| Effective suite list matches approved order | [Owner] | Pass / Fail | [Time] | [Link] |
| TLS 1.2 handshake succeeds | [Owner] | Pass / Fail | [Time] | [Link] |
| TLS 1.3 succeeds on Server 2022/2025 | [Owner] | Pass / Fail / N/A | [Time] | [Link] |
| Inbound business transaction succeeds | [Owner] | Pass / Fail | [Time] | [Link] |
| Outbound dependencies succeed | [Owner] | Pass / Fail | [Time] | [Link] |
| Load balancer / proxy paths healthy | [Owner] | Pass / Fail / N/A | [Time] | [Link] |
| Schannel and application logs clean | [Owner] | Pass / Fail | [Time] | [Link] |
| Security rescan passes | [Owner] | Pass / Fail | [Time] | [Link] |
| Rollback tested or validated | [Owner] | Pass / Fail | [Time] | [Link] |

# Windows quick checks

Effective suites: Get-TlsCipherSuite ¦ Select-Object -ExpandProperty Name

HTTPS: curl.exe -v https://service.example.org/

Schannel events: Get-WinEvent -FilterHashtable @{LogName='System'; ProviderName='Schannel'; StartTime=(Get-Date).AddHours(-2)}

# Linux quick checks

TLS 1.2: openssl s_client -connect service.example.org:443 -servername service.example.org -tls1_2 -cipher 'ECDHE-RSA-AES256-GCM-SHA384:ECDHE-RSA-AES128-GCM-SHA256'

TLS 1.3: openssl s_client -connect service.example.org:443 -servername service.example.org -tls1_3 -ciphersuites 'TLS_AES_256_GCM_SHA384:TLS_AES_128_GCM_SHA256'

Page 5 - Rollout Waves

Windows application servers first; domain controllers last.

| Phase | Scope | Planned window | Owner | Entry criteria | Status | Go / no-go decision |
| --- | --- | --- | --- | --- | --- | --- |
| 0 | Governance and GPO review | [Date] | [Owner] | Baseline and rollback approved | Not started | [Decision] |
| 1 | Lab: Server 2019/2022/2025 | [Date] | [Owner] | GPOs created and narrowly scoped | Not started | [Decision] |
| 2 | Representative application pilots | [Date] | [Owner] | Owners and tests confirmed | Not started | [Decision] |
| 3 | Non-production Windows | [Date] | [Owner] | Pilot success | Not started | [Decision] |
| 4 | Production application waves | [Date] | [Owner] | Owner sign-off and rollback ready | Not started | [Decision] |
| 5 | Windows infrastructure | [Date] | [Owner] | Application waves stable | Not started | [Decision] |
| 6 | Domain-controller pilot | [Date] | [Owner] | LDAP/LDAPS inventory complete | Not started | [Decision] |
| 7 | Remaining domain controllers | [Date] | [Owner] | 72-hour DC pilot stable | Not started | [Decision] |
| 8 | Closure and enterprise rescan | [Date] | [Owner] | All production waves complete | Not started | [Decision] |

# Wave rules

[ ] Do not promote a wave with an unresolved critical application failure.

[ ] Observe production application waves for 24-72 hours, adjusted for transaction frequency.

[ ] Keep low-frequency jobs open until their next normal execution.

[ ] Observe the pilot domain controller for at least 72 hours and a representative business cycle.

[ ] Do not re-enable TLS 1.0 or TLS 1.1 as a rollback measure.

Page 6 - Domain Controller Readiness

Dedicated controls for LDAPS, Global Catalog TLS, authentication, and directory dependencies.

| DC / site | OS | Role / criticality | LDAPS / GC consumers | Pilot ring | Owner | Status | Evidence |
| --- | --- | --- | --- | --- | --- | --- | --- |
| [DC] | [2019/2022/2025] | [Role] | [Apps/devices] | Pilot / Wave | [Owner] | Not started | [Link] |
| [DC] | [2019/2022/2025] | [Role] | [Apps/devices] | Pilot / Wave | [Owner] | Not started | [Link] |
| [DC] | [2019/2022/2025] | [Role] | [Apps/devices] | Pilot / Wave | [Owner] | Not started | [Link] |

# Pre-change

[ ] Inventory LDAPS 636 and Global Catalog TLS 3269 consumers.

[ ] Identify Linux LDAP clients, Java applications, appliances, identity products, monitoring, backup, and vendor integrations.

[ ] Validate DC certificates, chain, names, expiration, and private-key access.

[ ] Test a real authenticated bind and directory query; do not rely on a port check.

[ ] Confirm DNS, time, replication, SYSVOL, authentication, and monitoring health.

[ ] Confirm emergency access and GPO rollback authority.

# Post-change

[ ] Run dcdiag.exe /e /c.

[ ] Run repadmin.exe /replsummary and repadmin.exe /showrepl * /errorsonly.

[ ] Validate LDAPS and Global Catalog TLS from representative Windows and Linux clients.

[ ] Validate identity, federation, synchronization, certificate, backup, and monitoring products.

[ ] Record observation results and the go/no-go decision before the next DC wave.

Page 7 - Actions, Decisions, Risks, and Exceptions

Use these logs during weekly follow-up and change windows.

# Action log

| ID | Action | Owner | Due | Status | Evidence / notes |
| --- | --- | --- | --- | --- | --- |
| A-001 | [Action] | [Owner] | [Date] | Open | [Link / notes] |
| A-002 | [Action] | [Owner] | [Date] | Open | [Link / notes] |
| A-003 | [Action] | [Owner] | [Date] | Open | [Link / notes] |

# Decision log

| ID | Decision | Date | Decision owner | Rationale / evidence |
| --- | --- | --- | --- | --- |
| D-001 | Approve strong GCM-only baseline | [Date] | [Owner] | [Evidence] |
| D-002 | [Decision] | [Date] | [Owner] | [Evidence] |

# Risk and exception log

| ID | Application / connection | Required legacy behavior | Business impact | Compensating control | Owner / expiry | Status |
| --- | --- | --- | --- | --- | --- | --- |
| E-001 | [App / flow] | [Suite / limitation] | [Impact] | [Control] | [Owner / date] | Open |
| E-002 | [App / flow] | [Suite / limitation] | [Impact] | [Control] | [Owner / date] | Open |

Exception rule: Preserve TLS 1.2, add only the minimum necessary suite to the minimum necessary hosts, require security approval, and assign a remediation owner and expiration date.

Page 8 - Communications Tracker

Track each application-owner notice and response.

| Application / group | Owner | Initial notice | Response due | Pilot notice | Production reminder | Completion | Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| [App / group] | [Owner] | [Date] | [Date] | [Date] | [Date] | [Date] | [Notes] |
| [App / group] | [Owner] | [Date] | [Date] | [Date] | [Date] | [Date] | [Notes] |
| [App / group] | [Owner] | [Date] | [Date] | [Date] | [Date] | [Date] | [Notes] |
| [App / group] | [Owner] | [Date] | [Date] | [Date] | [Date] | [Date] | [Notes] |

# Core owner message

Why: Security scans identified weak or deprecated cipher suites. The change restricts Windows Schannel to modern AES-GCM suites with forward secrecy.

Expected impact: Supported modern clients should continue to work. Older runtimes, appliances, proxies, or hard-coded TLS configurations may fail if they cannot negotiate ECDHE with AES-GCM under TLS 1.2.

Owner action: Inventory inbound and outbound TLS paths, verify runtime and proxy support, remove hard-coded legacy suites, and execute the complete business transaction during testing.

# Communication assets

[ ] Initial owner notice - stored in Application-Owner-TLS-Cipher-Change-Communications.md

[ ] Pilot participation request - stored in Application-Owner-TLS-Cipher-Change-Communications.md

[ ] Production reminder - stored in Application-Owner-TLS-Cipher-Change-Communications.md

[ ] Completion notice - stored in Application-Owner-TLS-Cipher-Change-Communications.md

[ ] Domain-controller / LDAPS readiness notice - stored in Application-Owner-TLS-Cipher-Change-Communications.md

Page 9 - Rollback and Incident Notes

Use during a failed test or production change.

# Rollback sequence

Stop the affected rollout ring.

Capture timestamp, source, destination, port, application error, Schannel event, and failed transaction.

Disable or unlink the scoped cipher-order GPO, or apply the approved rollback GPO.

Run gpupdate /force.

Reboot affected systems under the service recovery plan.

Confirm the previous effective suite order.

Re-test the failed business transaction.

Create a time-limited compatibility exception and remediation action.

Do not: Do not re-enable TLS 1.0 or TLS 1.1 globally. Treat an incompatible client as a narrow application exception.

# Incident notes

| Field | Entry |
| --- | --- |
| Incident / change ID | [ID] |
| Detected | [Date / time / timezone] |
| Affected service | [Application / server / connection] |
| Symptoms | [Exact error] |
| Evidence | [Links] |
| Rollback initiated | [Date / time / approver] |
| Service restored | [Date / time] |
| Root dependency | [Legacy behavior / owner] |
| Remediation | [Action / due date] |

Page 10 - Closure Checklist and References

Complete before closing the program or change record.

[ ] Every in-scope server has the correct OS-scoped GPO.

[ ] Every in-scope application has owner sign-off or an approved unexpired exception.

[ ] The enterprise security rescan is clean or reconciled.

[ ] Domain controllers and LDAPS/Global Catalog TLS dependencies are validated.

[ ] Low-frequency scheduled jobs have completed successfully.

[ ] Before/after suite output, GPO reports, scan evidence, and test records are archived.

[ ] Exceptions have remediation owners, target dates, and expiration dates.

[ ] Operational ownership and periodic review cadence are assigned.

[ ] Lessons learned and future Linux hardening work are recorded.

# Microsoft references

| Reference | URL |
| --- | --- |
| Schannel cipher-suite index | https://learn.microsoft.com/en-us/windows/win32/secauthn/cipher-suites-in-schannel |
| Server 2019 / Windows 10 v1809 | https://learn.microsoft.com/en-us/windows/win32/secauthn/tls-cipher-suites-in-windows-10-v1809 |
| Windows Server 2022 | https://learn.microsoft.com/en-us/windows/win32/secauthn/tls-cipher-suites-in-windows-server-2022 |
| Windows Server 2025 and later | https://learn.microsoft.com/en-us/windows/win32/secauthn/tls-cipher-suites-in-windows-server-2025 |
| Manage TLS in Windows Server | https://learn.microsoft.com/en-us/windows-server/security/tls/manage-tls |
| Custom cipher-suite ordering | https://learn.microsoft.com/en-us/troubleshoot/windows-server/windows-security/deploy-custom-cipher-suite-ordering |
| NIST SP 800-52 Rev. 2 | https://csrc.nist.gov/pubs/sp/800/52/r2/final |

# Related team artifacts

Microsoft-Schannel-Cipher-Hardening-Rollout-Plan.md - authoritative detailed rollout plan.

Application-Owner-TLS-Cipher-Change-Communications.md - reusable owner notices.

This DOCX - collaborative follow-up runbook for OneNote or Teams use.